## Sheet1
Justice and Peace Strategic Work Plan 2015 to 2020
Democratic Governance and Inclusive, Participatory Decision-Making at all levels:
Outcome 1 : Improved governance in local government institutions and communities through the active participation of men, women and children in the decision making processes at all levels
Indicator 1. Number of councils that include and implement recommendations from women, men and children in their development plans.
Time frame
Output |  | Output indicator | Baseline | Target | Planned Activities | Year one |  |  |  | Year two |  |  |  | Year three |  |  |  | Year four |  |  |  | Year five |  |  |  | Amount
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 1.1 In at least 10 communities 50% more community members actively participate in the sessions of the local council and report about the outcomes to the communities. | 1.1.1 | # of reports to communities |  | 150 | Baseline survey on democratic processes and decision making in households, church groups, local councils, and community participation in decision making | bar: Year one Q1
| 1.1.2 | # of active contributions |  | 20 contributions per community | Design an action plan, design sensitization layout and input on democratic good governance and decision making | bar: Year one Q1 to Year one Q2
| 1.1.3 | # of people attending council sessions |  | 200 | identify facilitators and train them plus parish JPC to sensitize and follow up with communities | bar: Year one Q2; Year two Q1; Year three Q1; Year four Q1; Year five Q1
Sensitization and education on democratic governance and decision making in all parishes | bar: Year one Q2 to Year five Q4
Select and carry out intensive sensitization with target communities | bar: Year one Q2 to Year two Q1
Mobilize communities to attend council sessions | bar: Year one Q2 to Year four Q3
Continuous mobilization and follow-up | bar: Year one Q1 to Year four Q3
Follow up of active facilitators and parish JPC members | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
1.2. At least 10 community forums with at least 1/3 female members and at least 1/5 children’s representatives regularly discuss burning local issues, draft recommendations and dialogue with elected officials and duty bearers about the solutions and follow up on them. | 1.2.1 | # of community forums with at least 1/3 women and at least 1/5 children’s representatives created |  | 16 forums per council per year | Sensitization and mobilization of communities | bar: Year one Q2 to Year five Q3
| 1.2.2 | number of issues about which recommendations were made, |  | 8 per community per year | Preparatory sessions with children on children's councils and women leaders | bar: Year one Q2 to Year one Q3; Year two Q1 to Year two Q2; Year two Q4 to Year three Q1; Year three Q3 to Year three Q4; Year four Q2 to Year four Q3; Year five Q1 to Year five Q2; Year five Q4
| 1.2.3 | number of children and women ideas represented in recommendations |  | 50 | Following -up on women and children to attend council sessions with recommendations, discussions with authorities to table burning issues | bar: Year one Q4 to Year five Q4
| 1.2.4 | Number of engagements between the community forums and relevant local authorities resulting in the agreement of action plans to tackle the issues |  | 4 per community per year | Children's councils meetings with media and other authorities | bar: Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year three Q3; Year four Q1; Year four Q3; Year five Q1; Year five Q3
| 1.2.5 | actions taken according to the action plans |  | 80% | Provide feed back to communities and continuous mobilization of communities | bar: Year one Q3; Year two Q2; Year three Q1; Year three Q4; Year four Q3; Year five Q1; Year five Q3
Training and accompanying facilitators and JPC parish members to work with Church groups | bar: Year one Q1 to Year one Q2; Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
Follow up of active facilitators and parish JPC members | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
1.3 35% of church groups in the Archdiocese of Bamenda practice the rule of law, separation of power and regular, free and fair elections to install a culture of democracy | 1.3.1 | # of church groups which have revised their internal procedures and policies |  | 30 groups | Mobilization, sensitization and education sessions with Church groups | bar: Year one Q2 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
| 1.3.2 | percentage of groups that ask JPC to monitor their elections |  | 50% groups | Mobilization and sensitization of church groups | bar: Year one Q2 to Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year three Q3; Year four Q1; Year four Q3; Year five Q1; Year five Q3
| 1.3.3 | % of church groups whose internal procedures and policies fully reflect democratic norms |  | 80% of the targeted church groups | Continuous follow-up in church groups | bar: Year one Q2; Year two Q1; Year three Q1; Year four Q1; Year five Q1
1.4. 300 women are empowered in leadership and management roles in 10 council areas within the archdiocese to enable them to contest for elective and appointive positions in the church and local government. At least 50 of those women will be elected or appointed to such positions. | 1.4.1 | number of targeted women in leadership positions |  | 50 over the whole period | Selection of 10 council areas and identification of 300 female leaders | bar: Year one Q1; Year three Q1; Year five Q1
education of council leaders, councilors and women leaders on participatory democracy, mainstreaming gender into development projects and decision making processes and advocacy skills | bar: Year one Q2; Year two Q2; Year three Q2; Year four Q2; Year five Q2
Accompanying women leaders with intensive education on leadership skills, advocacy, gender and women in decision making | bar: Year one Q2 to Year one Q3; Year two Q2; Year three Q1; Year three Q4; Year four Q3; Year five Q2
1.5 In at least 10 parishes, paralegals of the JPC accompany the proceedings of the land consultative board by advising the complainants about the proper procedures and by monitoring and reporting about the hearings in order to reduce corruption. | 1.5.1 | Number of clients / complainants sensitized on the effects of corruption and advised on the correct proceedings of the land consultative board per parish |  | 5 per parish per annum | Identification of target parishes, identification of land consultative boards and collection of baseline data | bar: Year one Q3; Year two Q3; Year three Q3; Year four Q3; Year five Q1; Year five Q3
sensitize communities on transparent and non corrupt methodologies on land dispute settlement | bar: Year one Q3; Year two Q3; Year three Q3; Year four Q3; Year five Q3
design an action plan, and follow up procedures with land consultative board | bar: Year one Q3 to Year one Q4; Year two Q3 to Year two Q4; Year three Q3 to Year three Q4; Year four Q3 to Year four Q4; Year five Q3 to Year five Q4
| 1.5.2 | number of meetings attended per parish and year |  | 5 meetings per parish per year | Feedback and more follow up
1.6 In 15 communities at least 150 fathers will act as real partners of their wives in all aspects in the upbringing of their children including decision making. | 1.6.1 | Testimonies on change stories of fathers, mothers and children |  | 2 testimonies per father per year | collect data on gender roles in decision making, child upbringing and sharing of household responsibility in 15 communities | bar: Year one Q1
| 1.6.2 | Examples of changes in joint decision making of the sexes in the family and community organizations due to project activities |  | 2 changes per community per year | design sensitization and education on gender and decision making, gender perspectives in household responsibilities and child upbringing | bar: Year one Q1
Train trainers and disseminate seminar in communities around the archdioses | bar: Year one Q1 to Year one Q4
Follow up on active trainers and their activities in parishes | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
Identification of target communities and intensive education and follow -up on implementation | bar: Year one Q2; Year two Q2; Year three Q2; Year four Q2; Year five Q2
Inter-community events to share experiences | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
More feed back and intensification of activities | bar: Year three Q1; Year four Q1; Year four Q3; Year five Q1; Year five Q3
Accompanying communities to provide feed back to general public | bar: Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year four Q2; Year five Q3
Evaluation of first phase project | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q3
1.7 In at least 10 communities Children’s Councils regularly discuss burning child rights issues with the relevant authorities and through media with the public. They contribute to the implementation and follow up on the action plans that they develop with the authorities. | 1.7.1 | Number of engagements between the Children’s Councils and relevant authorities resulting in the agreement on strategies and action plans to tackle the issues |  | 10 per community per year | Collect data on child right situation and participation in community activities | bar: Year one Q1
Design sensitization seminar on child rights and participation | bar: Year one Q1 to Year one Q2
Identify and train facilitators and parish JPC, disseminate education and sensitization in all parishes and with council authorities | bar: Year one Q2 to Year one Q4
Identify target communities, target councils and target children for intensive education | bar: Year one Q2 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
Follow up activities of trained facilitators and parish JPC members | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
Design plan of action with authorities and communities | bar: Year one Q2
| 1.7.2 | number of discussions held |  | 20 Per year and per community | Accompanying children to dialogue and table recommendations to authorities | bar: Year one Q3 to Year five Q4
Media education and campaigning on child rights and activities of Children Councils in media | bar: Year one Q3; Year two Q1; Year two Q3 to Year two Q4; Year three Q2; Year three Q4; Year four Q2; Year four Q4; Year five Q2; Year five Q4
| 1.7.3 | % of implementation of action plans |  | 50% | Monitoring and follow-up of project | bar: Year one Q2; Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4; Year four Q2; Year four Q4; Year five Q2; Year five Q4
Evaluation of first phase of project | bar: Year one Q4; Year three Q4; Year five Q4
Identification of next set of target, education and follow up | bar: Year two Q1; Year three Q1; Year four Q1; Year four Q4; Year five Q4
Key Result Area 2: Constructive Conflict Management and dispute Settlement
Outcome 2: Violence is prevented through early responses to and constructive management of conflicts
Outcome indicator 1 a): 40% reduction in the number of household/inter-village/inter-tribal conflicts in the archdiocese
Indicator b)% increase in frequency and type of interaction between members of conflicting communities | [5 empty] | Year one Q1: Time frame
[6 empty] | Year one Q1: Year one; Year two Q1: Year two; Year three Q1: Year three; Year four Q1: Year four; Year five Q1: Year five | Amount
Output |  | Output indicator | Baseline | Target | Planned activities | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
2.1 Land disputes between four villages will be managed by joint committees, of which at least every third member is female and where at least two representatives of children and youth are included. | 2.1.1 | Proportion of male to female |  | one is to three | collect data on village land dispute resolution processes, design intervention mechanisms that aim at reducing corruption, mainstreaming gender in peace processes, importance of involving women and children in dispute and decision making processes | bar: Year one Q1 to Year one Q2
Identify and train facilitators and parish JPC, disseminate education and sensitization in all parishes, | bar: Year one Q2 to Year one Q3
Follow up activitiesa of active trained facilitators and parish JPC | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
identify target villages and intensify education and design mechanisms to include women and children voices in proccesses, creation of joint dispute resolution committees and line of action | bar: Year one Q3; Year two Q1; Year three Q1
| 2.1.2 | Number of children in the committees |  | 4 per committee | Intensive education, coaching and mentoring JPC activities with joint committees | bar: Year one Q3 to Year one Q4; Year two Q2 to Year two Q3; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
| 2.1.3 | number of joint strategies and action plans developed |  | 5 strategies per village per year | Monitor and follow-up activities of joint land dispute resolution committees | bar: Year one Q4
| 2.1.4 | % of action points from plan implemented in time |  | 70% timely implementation rate | Evaluation of activity and identification of next target villages for the activity | bar: Year one Q4 to Year two Q1; Year three Q1; Year four Q1; Year five Q1
2.2 Joint committees of pastoralist and farmers are mediating their own disputes in at least two divisions with the active participation of women and youths and children representatives | 2.2.1 | Evidence fo committees established |  |  | Continuous follow-up of joint land dispute resolution committees | bar: Year two Q1; Year two Q3; Year three Q1; Year three Q3; Year four Q1; Year four Q3; Year five Q1; Year five Q4
| 2.2.2 | % of women and children included |  | 1 is to 3 ratio of female to male members, 5 children representative committee | Initial contact meetings with pastoralists and farmers separately, identification of root causes of disputes and consequences and possibility to meet jointly for discussions | bar: Year one Q2
| 2.2.3 | Contributions of women and children during deliberations and responses to them |  | 1/4 of all contributions are from women, youth and children | design education on alternative dispute resolution and importance of using constructive conflict mediation, conflict transformation approaches and stressing negative effects of former approaches and reasons for past failures in former methods | bar: Year one Q1 to Year one Q2
Identify and train facilitators and parish JPC members who will disseminate education and follow up activities of joint committees | bar: Year one Q1 to Year one Q2
Follow up activities of active trained facilitators and parish JPC | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
| 2.2.4 | Proportion of violently escalated conflicts and cofnlcits with high risks of escalation between pastoralists and farmers for which a solution has been proposed by the committees |  | 5 per year per community | Carryout an analysis of the situation with farmers and pastoralists in a joint workshop that uses JPC method of work, Carryout an intensive social analysis with greater population and draw a plan of action that will reduce corruption, increase the voice of women and children, uses more of alternative dispute resolution approaches | bar: Year one Q3 to Year one Q4; Year two Q3 to Year two Q4; Year three Q3 to Year three Q4; Year four Q3 to Year four Q4; Year five Q3 to Year five Q4
| 10 | Reduction in number of cases between pastoralists and farmers brought to the courts from those communities |  | 50% decrease | Create joint committees 1) dispute resolution committee, assessment committee, advisory and supervisory committee and carryout intensive training with them | bar: Year one Q3 to Year one Q4; Year three Q1 to Year three Q2; Year five Q1 to Year five Q2
facilitators and parish JPC members accompany the activities of joint committess with coaching, mentoring, and monitoring
Monitoring and follow-up of project | bar: Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year three Q3; Year four Q1; Year four Q3; Year five Q1; Year five Q3
Identification of the communities | bar: Year one Q3; Year two Q3; Year three Q3; Year four Q3; Year five Q3
2.3 80% Youth Peace Committees male and female constructively manage disputes among young people and prevent escalation through early warning and response and channeling burning issues of the youth to authorities and engage their peers in peace education in at least 10 communities | 2.3.1 | Number of disputes handled among young people |  | 10 per year per community, | Initial contacts with youths, women, men and traditional authorities, education authorities etc in the community and all social groups existing in the community | bar: Year one Q1; Year three Q1; Year five Q1
Inform community members and all social groups to understand the expected results and project activities and to know all the targeted villages and the outcome of the project | bar: Year one Q2; Year two Q2; Year three Q2; Year four Q2; Year five Q2
| 2.3.2 | Number of conflicts prevented and types of response methods used |  | 10 per year per community, two early warning mechanism used | collection of data on types of violence, conflicts and disputes in the community, holding separate meetings with social groups and all stakeholders and holding joint meetings later on in the course of the project | bar: Year one Q2 to Year one Q3
Design workshop layouts on ADR, constructive conflict management, gender and peace building, inclusion of youth, children and women in processes, peace, respect and tolerance among peers for students and pupils, etc | bar: Year one Q1 to Year one Q2; Year two Q1 to Year two Q2; Year three Q1 to Year three Q2; Year four Q1 to Year four Q2; Year five Q1 to Year five Q2
Training facilitators and JPC parish members on workshop facilitation and on the results to be attained by the project | bar: Year one Q2
Holding joint meetings with youth, men, women, authorities etc | bar: Year one Q2; Year two Q1; Year two Q4; Year three Q3; Year four Q2; Year five Q1
Holding intensive workshops in joint groups on peace building and creation of committees- youth peace committees, Women peace building committees will be intensified in the new approach, men peace committees created, setting of roles and responsibility of the authorities. | bar: Year one Q2 to Year five Q4
| 2.3.3 | Number of issues channeled to authorities and number of response from authorities |  | 3/community/year; 2/3 positive response | desiging roles and responsibilities of each and jointly agreeing on these roles and responsibilities | bar: Year one Q2 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
| 2.3.4 | Number and frequency of peace education held with peers within same community and with YPC of other neighboring communities |  | 12 per year among peers and 6 per year among adversary community | Intensive education, coaching and mentoring JPC activities with joint committees and drawing a line of action of each committee and a joint line of action of all the groups | bar: Year one Q3 to Year five Q4
| 2.3.5 | Number, frequency and type of interactions/sporting events with peer YPC of other communities |  | 6 per year every 2 months on peace education workshop/sensitization, sporting events and income generating activities exchange sessions | design and organize intensive activities with youth peace building committees in each community engaging them in income generating activities | bar: Year one Q3 to Year one Q4; Year two Q3 to Year two Q4; Year three Q3 to Year three Q4; Year four Q3 to Year four Q4; Year five Q3 to Year five Q4
2.4 50% of YPC engage in income generating activities and have increased their livelihood by 30% | 2.4.1 | 30% increase in lielihood of YPC members |  | 30% increase | Organize inter-village sporting events , workshops and quizzes between adversary villages | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
2.5 80% of women Peace Committees constructively settle disputes in the households and quarters, they prevent violence on the different levels up to the inter-village disputes by early warning and response in at least 10 villages | 2.5.1 | number, frequency and type of disputes handled |  | 12 per year monthly, houshold and quarter violence | Extended media coverage for these events and sharing in other villages to learn from others | bar: Year one Q3 to Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
| 2.5.2 | frequency of using early warning response mechanisms
2.6 70% WPC engage with the men's committees to raise burning issues with the authorities so that the root causes of conflicts will be tackled before the conflicts escalate in at least 10 villages | 2.6.1 | number and frequency of joint meetings |  | Monthly | Follow up on such events and monitor and evaluate | bar: Year one Q2; Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4; Year four Q2; Year four Q4; Year five Q2; Year five Q4
| 2.6.2 | number and type of ideas raised by joint committees to authorties
| 2.6.3 | number and type of responses that authorities are acting on
2.7 75% of WPC are advocating together for the respect of women's rights in at least 10 communities | 2.7.1 | Number and types of women rights issues raised to authorities |  | 3 per year, quarterly | Organize and implement peace education in schools in formal settings | bar: Year one Q1 to Year five Q4
| 2.7.2 | Number of women right issues authorities has given positive solutions to.
Evidence that 10% of WPC members are enjoying at least one of their rights
2.8 75% WPC with their spouses create more peaceful homes with less violence against women and children in at least 10 villages | 2.8.1 | Evidence that violence geared at women and children in homes have reduced by 50% |  | 5 per year on women's rights and decision making | Organize inter-school events , quizzes and sporting events and music competitions | bar: Year one Q2 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
| 2.8.2 | Testimonies from women and children
2.9 75% WPC engage in joint economic activities and have increased their contriution to family income by in at least 10 communities | 2.9.1 | Number and type of economic activities of WPC |  | 2/3 positive responses | Follow-up on youth dispute settlement skills for intensive training and mentoring | bar: Year one Q3; Year two Q2; Year three Q1; Year three Q4; Year four Q3; Year five Q2; Year five Q4
| 2.9.2 | Evidence of a 10% increase in family spending
| 2.9.3 | Number and frequency of interactions for economic activity purposes between WPCs of neighboring villages
2.10 75% Men Peace Committees constructively settle disputes in the households and quarters in at least 10 villages | 2.10.1 | number and types of of disputes handled |  | 5 issues per year on HTP against women | Train women and men committees on ADR, inclusion of men and women communittees in discusions with authorities on root causes of conflicts and consequences and ways to reconcile all parties | bar: Year one Q2 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
2.11 75% MPC prevent violence on the different levels up to inter-village disputes by early warning and response in at least 20 villages | 2.11.1 | Number, type and frequency of early warning response used |  | 3 out of 5 | Involve women in income generating activities | bar: Year one Q2 to Year one Q4; Year two Q2 to Year two Q4; Year three Q2 to Year three Q4; Year four Q2 to Year four Q4; Year five Q2 to Year five Q4
2.12 20% MPC of 10 villages advocate for the active participation of women in public decision making and peace building | 2.12.1 | Type of campaign messages disseminated and target audience |  | 10% of women enjoy at least one of their right | Follow-up on these economic empowerment activities | bar: Year one Q4 to Year five Q4
| 2.12.2 | Evidence that 1/3 WPC members participate in public decision making and peace building processes |  |  | Engage women and men in inter-village interactions in prayer sessions, social and economic activities | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
2.13 50% MPC and WPC members together with their spouses create more peaceful homes where women participate more equally in the household decisions and where violence against women and children is drastically reduced in 20 villages | 2.13.1 | Testimonies from women, men and children of reduced violence in homes |  | 50% reduction of violence in homes | Organize and hold meetings with traditional rulers, men, women and youth to assess progress of the model | bar: Year one Q1; Year one Q3; Year two Q1; Year two Q3; Year three Q2; Year four Q1; Year four Q4; Year five Q4
| 2.13.2 | Evidence of cohesive homes with equally sharing of tasks and joint decision making |  | 50% homes in 20 villages
2.14 80% local authorities in 10 villages constructively settle disputes aiming at reconciliation. They encourage the active participation of women and youth in disputes resolution and peace building proccesses and form dispute settlement fora that bring together the adversaries to jointly find amicable solutions | 2.14.1 | Number and type of joint dispute settlement efforts organized and attended by Fons of conflicting villages |  | 3 joint meetings per village per year to settle land/boundary disputes | Organize and hold discussions with authorities, men and women on harmful traditional practices against women, women in decision making and women's access to land and inheritance and other burning women's rights issues in the community | bar: Year one Q1 to Year one Q3; Year two Q2 to Year two Q3; Year three Q2 to Year three Q3; Year four Q2 to Year four Q3; Year five Q2 to Year five Q3
| 2.14.2 | Evidence that 1/3 members of dispute settlement committee members are women and youth representatives have contributed ideas |  | 1/3 members are women, youth are represented in meetings and contribute ideas | Draw line of action and follow-up on implementation | bar: Year one Q1 to Year five Q4
| 2.14.3 | Evidence that ideas of women and youth form part of the final recommendations in the dispute settlement |  | ¼ recommendations reflect contributions from women and youth of all dispute settlement resolutions | Organize more inter-village events and involving traditional rulers from conflicting villages. | bar: Year one Q3 to Year one Q4; Year two Q3 to Year two Q4; Year three Q3 to Year three Q4; Year four Q3 to Year four Q4; Year five Q3 to Year five Q4
| 2.14.4 | Evidence that reconciliatory rites etc have been conducted between adversaries that confirm parties have reconciled |  | 4 reconciliatory mechanisms entered into by conflicting factions of 4 tribes each year. | Develop strategies to reconcile conflicting communities | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
Monitor and report on this project- separately and jointly | bar: Year one Q1; Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year three Q3; Year four Q1; Year four Q3; Year five Q1; Year five Q3
Carry out a participatory evaluation of the model separately with each committee and jointly with representative from all committees | bar: Year one Q4 to Year two Q1; Year three Q1 to Year three Q2
Evaluate all the participating villages and share experiences and lessons learnt from the model | bar: Year three Q2 to Year three Q3; Year five Q3 to Year five Q4
Share feedback to all and design way forward | bar: Year three Q4; Year five Q4
Key Result Area 3: Supporting the most vulnerable groups to realize their rights
Outcome 3.1: Trafficking is further reduced and the most vulnerable groups are empowered and their rights better protected.
Outcome indicator 3.1: 80% more victims of trafficking in persons in the archdiocese supported and rehabilitated
Outcome Indicator 3.2: 60% increase in business capital for vulnerable groups in 30 parishes of the archdiocese
Outcome Indicator 3.3: Evidence of 20% reduction of violence against women that occur in 20 parishes and actions taken by women and men to redress the situation
Outcome Indicator 3.4: 10% increase in the respect of rights of vulnerable persons in the justice, penitentiary systems and in archdiocesan institutions
Timeframe
[6 empty] | Year one Q1: Year one; Year two Q1: Year two; Year three Q1: Year three; Year four Q1: Year four; Year five Q1: Year five | Amount
Output |  | Output indicator | Baseline | Target | Planned Activities | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
3.1 50% of the 100 trained JPC workers render paralegal services in at least 30 parishes of the Archdiocese of Bamenda. | 3.1.1 | number of case files created and followed-up per paralegal |  | 12 cases per year per paralegal | advocate for pro bono support through additional barristers, identify paralegals and train, | bar: Year one Q1
Training of 100 paralegals on relevant laws, counselling, mediation and arbitration | bar: Year one Q2
More in-depth training of lead paralegals and deputies of the five division supporting selected cases at court by barristers, | bar: Year one Q2
Mentoring / coaching of lead paralegals and deputies by the JPC office and the barristers Supporting selected cases at courts by barristers | bar: Year one Q2 to Year three Q4
Use radio programs to sensitize the public about the program and the available support Monitoring | bar: Year one Q3 to Year three Q4
End of year: experience sharing, learning and networking events of the active paralegals per division | bar: Year one Q4; Year two Q4; Year three Q4
follow-up training for active paralegals and lead paralegals | bar: Year two Q1 to Year three Q4
after 6 months: experience sharing, learning and networking events of the active paralegals per division, evaluation of event in whole archdiocese | bar: Year two Q2; Year three Q2 to Year three Q4
Engage the catholic church for the continued basic funding of the paralegals follw up, training, networking and casework | bar: Year three Q4
3.2 10 vigilance committees formed in 10 villages are pre-empting trafficking in persons | 3.2.1 | Number of cases identified and reported to JPC |  | 3 cases per year per village | Train journalist and vigilance committee members, draw an action plan | bar: Year one Q1
|  | Number of pre-empted cases |  | 5 cases pre-empted per village per year | Media campaign around day of human trafficking, July 30 | bar: Year one Q2; Year two Q2; Year three Q2
Identification of volunteers and formation of vigilante groups Training of vigilante groups and development of activity plans and standard operational procedures (SOPs) – including reporting to the media – in the target communities | bar: Year one Q2
Follow up on cases of trafficking | bar: Year one Q2; Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4
| 3.3.2 | 10 media coverage on Trafficking in persons issues |  | 10 per year | Monitoring and follow-up on activity plans and SOPs Follow-up on cases of trafficking | bar: Year one Q3 to Year three Q4
| 3.3.3 | 70% accurate media report Trafficking in Persons |  | 70% | Annual learning, experience sharing and monitoring event for the vigilante groups | bar: Year one Q4; Year two Q4; Year three Q4
Follow-up training of vigilante groups, development of activity plans and adjustment of standard operational procedures (SOPs) in the target communities | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2
Final learning, experience sharing and evaluation event for the vigilance groups | bar: Year three Q4
3.4 At least 50 victims of trafficking are reunited with their families or have found a home with care-givers that adequately support them each year. | 3.4.1 | Number of victims identified who receive care |  | 50 each year | Training of community vigilante groups on counselling and accompanying victims and their families | bar: Year one Q1
Tracing of families of victims | bar: Year one Q1 to Year three Q4
3.5 At least 200 victims of trafficking are attending schools or skills trainings. At least 150 have started their own trade. | 3.5.1 | Enrollment figures in school institutions, number of established trades |  | 40 in school each year, 30 own a trade each year | Counselling of victims and families by vigilante groups and JPC project staff Supporting the schooling or skills trainings of survivors | bar: Year one Q1 to Year three Q4
Training of female care-givers of reintegrated survivors on income generating activities | bar: Year one Q2 to Year three Q3
Training of care-giving couples on joint management of household finances | bar: Year one Q2 to Year two Q3; Year three Q1 to Year three Q3
Monitoring of the reintegrated survivors and their families by community vigilante groups and JPC project staff | bar: Year one Q1; Year one Q3; Year two Q1; Year two Q3; Year three Q1; Year three Q3
Annual learning and experience sharing event of vigilante groups | bar: Year one Q4; Year two Q4; Year three Q4
3.6 At least 100 homes of victims of child labor have improved their economic situation through strengthened business skills (or other skills necessary for income generating activities) of the female care-giver and an improved, joint management household finances by male and female care-givers | 3.6.1 | 20% Increase in household income |  | 20 families each year 1:1 ratio of female to male household spending | Supporting schooling and or trade , training of care-giver or couple, monitoring and sharing of experiences, continuous support
3.7 40% of issues of illegal detention attended to by the JPC leading to a 10% reduction of illegal detention in the five prisons of the Archdiocese. | 3.7.1 | 40% of cases of illegal detention attended to |  | 40% cases per prison per year | Training of selected paralegals on attending to cases of illegal detention | bar: Year one Q1 to Year one Q4
Case work of paralegals on cases of illegal detention | bar: Year one Q1 to Year three Q4
after 6 months) Follow-up Training of active paralegals on attending to cases of illegal detention combined with learning, experience sharing and monitoring | bar: Year two Q2; Year two Q4
Monitoring and support the case work of paralegals through office and barristers | bar: Year one Q2 to Year three Q4
Learning, experience sharing and evaluation event of active paralegals | bar: Year one Q4; Year two Q4; Year three Q4
| 3.7.2 | 10% reduction of illegal detention |  | 10% per prison per year | Train selected paralegals on counselling of inmates and supporting reconciliation processes Selection | bar: Year one Q1
3.8 20% of inmates acquire life skills in the five prisons of the Archdiocese | 3.8.1 | number of trainings and of inmates trained |  | 4 trainings per year for 20 in-mates per prison | Training of trainers (facilitators) to implement trainings for JPCs in Parishes on supporting the former inmates and their families Facilitators: Train JPCs in Parishes (elected members, volunteers and paralegals) on counselling, referrals for the families of inmates, on organizing support for the families and the former inmates in the communities and on preparing the families for the reintegration of the inmates: develop standard procedures | bar: Year one Q1 to Year one Q2
| 3.8.2 | number of inmates that produce articles for sale |  | 20 per prison | Life skills training for inmates on income generating activities, anger management and communication skills Counselling of inmates to support process of remorse, apology and reconciliation by paralegals | bar: Year one Q1 to Year three Q4
| 3.8.3 | inmates targeted less frequently involved in violence |  | 50% in mates per year | Monitoring adherence to standard procedures | bar: Year one Q2; Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4
3.9. The JPCs will link at least 200 families of inmates to support structures and prepare them for the eventual reintegration of the inmates. | 3.9.1 | number of referrals to support structures |  | 40 Per year | Train paralegals, facilitators and parish JPCs on counseling, referrals for the families, ongoing organizing support for the families | bar: Year one Q1 to Year one Q4
Organization of economic activities and sales of inmates by paralegals supported by office | bar: Year one Q2 to Year three Q3
Training of active facilitators on implementing follow-up trainings | bar: Year two Q1 to Year two Q2; Year three Q1 to Year three Q2
| 3.9.2 | number of families prepared to receive their relative |  | 40 per year | Facilitators: Monitoring of adhering to standard procedures for the support of families by JPC members and volunteers | bar: Year one Q2 to Year one Q4
Follow -up training of active paralegals, JPC parish members and volunteers on the project | bar: Year two Q1; Year two Q3; Year three Q1; Year three Q3
Monitoring and support of work of paralegals and facilitators | bar: Year one Q1 to Year three Q4
Annual learning, monitoring and experience sharing event for active facilitators, JPCs members and volunteers and paralegals | bar: Year one Q4; Year two Q4; Year three Q3 to Year three Q4
Final learning and experience sharing and evaluation event for active facilitators, JPCs and paralegals | bar: Year three Q3 to Year three Q4
| 3.9.3 | Satisfaction of families with the service |  | 70% of the targeted families
3.10 Male and female members of 20 parishes are aware of the causes and consequences of (S)GBV and the available support services for survivors. | 3.10.1 | 50% target group who can identify and describe the causes and consequences including the support services |  | 25 members per parish per year | Collect data on(S)GBV and gender equality situation in the archdiocese, available services, design training package (seminar layout) | bar: Year one Q1
identify seminar facilitators and train facilitators and parish JPC members | bar: Year one Q1
disseminate seminar workshop on (S)GBV and gender equality in all parishes of archdiocese, identify target parishes for follow up | bar: Year one Q1 to Year one Q4
Intensive sensitization and education on SGBV in targeted parishes | bar: Year one Q2 to Year one Q3; Year two Q4; Year three Q4; Year four Q4
Mentoring and coaching of target and organizing sharing of experiences events, show case events in denearies | bar: Year one Q3 to Year one Q4; Year two Q4; Year three Q4; Year four Q4
Follow up and continuous education on SGBV | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4
3.11 In six deaneries 10 couples each act as role models in gender equality and showcase the positive effects of such a relationship. | 3.11.1 | list of actions/behaviour that show gender roles are being performed by each sex, |  | 10 couples per deneary per year | Identify target couples and intensify education with them on their roles and responsibilities in the project | bar: Year one Q1; Year two Q1; Year three Q1; Year four Q1; Year five Q1
Design gender roles and responsibilities for the target couples | bar: Year one Q1 to Year one Q3
organizing events to share experiences, events to show case their new found roles to the public | bar: Year one Q4
Monitoring and evaluation , continuous follow-up of couples | bar: Year one Q4 to Year two Q1; Year two Q4; Year three Q2; Year three Q4; Year four Q2; Year four Q4; Year five Q2; Year five Q4
| 3.11.2 | events to showcase positive effects |  | 1 per deneary per year | Organizing events to share experiences, events to show case their new found roles to the public | bar: Year one Q4; Year two Q4; Year three Q4; Year four Q4; Year five Q4
Media events to make public the role of couples | bar: Year one Q2 to Year two Q1
Identify next phase of target couples and intensify education with them on their roles and responsibilities in the project | bar: Year two Q1 to Year two Q2; Year two Q4 to Year three Q1; Year three Q4 to Year four Q1; Year four Q4 to Year five Q1; Year five Q4
3.12 The people in the Diocese are conversant with the importance of writing wills and 5% of them were accompanied to write their wills. 60% of the justice and peace workers have actually written their will. | 3.12.1 | 5% of the population accompanied to write their will |  | 5% population | Launch massive education campaign on the importance of writing wills, disseminate education | bar: Year one Q2 to Year one Q3
Accompanying persons to write will | bar: Year one Q2 to Year two Q1
| 3.12.2 | 60% of justice and peace workers with a written will |  | 60% JPC member | Monitor the process and evaluate | bar: Year one Q2 to Year two Q1
3.13 In four fondoms, the fons, the traditional councils and representatives of women’s groups have agreed upon strategies to minimize harmful traditional practices that violate women’s rights and are implementing them | 3.13.1 | strategies and plan of action developed |  | 1 Fondom per year | Design education on HTP against women, and how to reduce them, draw plan of action and identify target Fondoms | bar: Year one Q1
Training trainers and parish JPC members | bar: Year one Q2
disseminate seminar with Fons, traditional councils and women, men etc to reduce HTP against women, design strategies to reduce HTP against women | bar: Year one Q2 to Year two Q4
Develop and launch massive campaign on plan of action to minimize HTP, in media, etc | bar: Year one Q2 to Year three Q4
Follow up on recommendations, monitor, mentor and accompany women who are ready to effect change | bar: Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4 to Year five Q4
| 3.13.2 | Percentage of action points implemented |  | 40% implementation rate | Follow-up activities of Fons, men and women and the campaign | bar: Year one Q4; Year two Q2; Year two Q4; Year three Q2; Year three Q4
3.14 Information campaign messages on gender discrimination and harmful traditional practices against women is received and used by 30% population in 4 Fondoms by men, women and traditional leaders | 3.14.1 | 50% target group who can describe the campaign message |  | 50% | Intensify campaign, Follow up, coaching and mentoring of women, men and Fons to ensure change takes place | bar: Year one Q4 to Year two Q1; Year two Q3 to Year two Q4
| 3.14.2 | 30% target group who took action as a result of the campaign message or contacted a provider of/for information or services |  | 30% | Sharing of experiences, learning from each event, Monitoring and evaluation | bar: Year one Q4; Year two Q4; Year three Q4
3.15a 90% of the workers in the archdiocese have formal employment contracts according to the labour code. | 3.15.1a | Employment contracts |  | 90% | Continuous education, accompanying, follow up of archdiocesan workers situation, monitoring and evaluation | bar: Year one Q1 to Year four Q1
3.15b At least 50% of the poorly done contracts of the archdiocese will be reformulated to guarantee the worker’s rights. | 3.15.1b |  |  | 50%
Key Result Area 4: JPC Organizational Development
Outcome 4: JPC is a more effective and efficient organization, with improved systems and processes, well managed resources
Outcome indicator 4.1: % of JPC staff, volunteers, paralegals, elected JPC members surveyed who rate JPC favorably on empowerment and engagement | [5 empty] | Year one Q1: Timeframe
Output |  | output indicators | baseline | Target | Planned activities | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
4.1 In order to ensure an effective and efficient delivery of results as well as the sustainability of the organization, JPC leadership fosters a working environment with clear and transparent internal structures and processes, including: An organogram reporting lines, roles and responsibilities, knowledge management strategy, internal policies / code of conduct on gender, child protection, whistle blowing, finances etc | 4.1.1 | existence of approved and signed documents (see column one), |  | JPC documents development(see column one) 40 facilitators, 100 paralegals | Resource mobilization with the Strategic Plan documents and MTE report recommendations/ proposal writing | bar: Timeframe Q1 to Timeframe Q2
| 4.1.2 | plans of action for implementation, |  | 3 plans of actions | develop local resource mobilization strategies | bar: Timeframe Q1 to Timeframe Q2; Timeframe Q1 to Timeframe Q2; Timeframe Q1 to Timeframe Q2
| 4.1.3 | de facto behaviour of staff, JPC elected members, paralegals, facilitators and volunteers mirrors the codified agreements / documents |  | 100% compliance 100% delivery rate | Organize JPC staff retreat for organizational assessment of the past, self appraisal and reflection and gain deeper understanding and insight on the strategic plan to foster responsibility and ownership | bar: Timeframe Q1; Timeframe Q1; Timeframe Q1; Timeframe Q1; Timeframe Q1
Develop: • An organogram • clarify reporting lines, • clarify roles and responsibilities of technical arm and elected JPC members, • knowledge management strategy, • internal policies / code of conduct on gender, gender policy, child protection, whistle blowing, • develop communication lines at all levels, | bar: Timeframe Q1
 share organogram for feedback from archdiocesan authorities, Share all these systems for feedback from JPC elected members; | bar: Timeframe Q2
Intensify RBM with staff and implementing partners that is parish JPC, paralegals and facilitators; | bar: Timeframe Q2; Timeframe Q1; Timeframe Q1
4.2 Human resource management and capacity of JPC workers (staff, elected JPC members, paralegals, facilitators and volunteers) strengthened to ensure commitment and a talented, diversified and productive justice and peace workers at all levels in the archdiocese | 4.2.1 | % of trained JPC workers |  | 80% | Design specific seminar layouts on the general themes of the strategic plan including: • Good Governance Democracy and Decision Making; • Constructive Conflict Management and Dispute Resolution; • Respect for human rights in the justice process; • Counseling for in-mates and other vulnerable groups; • Democratic Leadership; • Human rights versus African Traditions and the Social Teaching of the Church; • Gender equality and Gender Based violence; • Women and Leadership; • Gender and Poverty Reduction; • Curbing HTP against Women; | bar: Timeframe Q1 to Timeframe Q2
4.3 Results based management is enhanced at all levels including programme effectiveness (planning, monitoring, evaluation and reporting) | 4.3.1 | % of JPC paralegals, staff, elected members and facilitators producing results based focused report |  | 90% |  Identify paralegals and facilitators and train them on method work of justice and peace, role and mandate of the commission, participatory facilitation skills and approaches; Plan for a more targeted training with these groups on the above mentioned seminar themes to be designed | bar: Timeframe Q1 to Timeframe Q2; Timeframe Q1 to Timeframe Q2
| 4.3.2 | Rate of implementation of evaluation recommendations |  | 100% | Monitor and follow-up on their activities | bar: Timeframe Q2; Timeframe Q4; Timeframe Q2; Timeframe Q4; Timeframe Q2; Timeframe Q4; Timeframe Q2; Timeframe Q4; Timeframe Q2; Timeframe Q4
4.4 JPC financial sustainability ensured (i) enhanced and diversified resource mobilization partnership base (ii) local mobilization strategies developed and implemented | 4.4.1 | Strategy developed and resources raised |  | 3 strategies
| 4.4.2 | Amount raised from (i)foreign donors (ii) local contribution
4.5 Communication strategies developed and implemented that lead to improved awareness of JPC role and mandate among targeted partners, elected JPC members, JPC paralegal, facilitators and all stakeholders | 4.5.1 | Reach by JPC to its targeted stakeholders through: a. JPC website b. JPC social media channels c. Conventional media coverage (i.e. TV/print/web media articles) |  | 2 TV interviews per annum/ 4 print interviews per annum/4 web articles per annum | bar: Timeframe Q1